Smart Parking Platform

# 1.Existing Software Landscape

- ParkMobile – used for on-street payment in partnership with cities but focuses on payment processing rather than occupancy analytics or structured garage reservations.

- Passport – municipal parking platform used by cities for curbside and city-managed parking. It is good when it comes to enforcement and compliance but is more of a broad municipal solution than a platform tailored for real-time garage availability and garage reservations.

- SpotHero –  large parking marketplace that connects drivers with parking locations across many cities. It is designed around helping users find and book parking for individual trips instead of supporting long-term integration with a city’s parking operations.

- ParqEx – smaller parking platform focused on garage access, billing, and reservations. Works well at the facility level but it does not appear to offer the same level of citywide occupancy analytics or ordinance-based pricing that a transportation department may need.

Differentiation: Existing platforms tend to prioritize individual garage access and reservations, municipal payment services, or large-scale parking marketplaces. What SmartPark brings to the table is being designed specifically for one city’s downtown garage network. That allows the system to prioritize city-specific requirements and integration with existing municipal payment infrastructure instead of trying to serve many different markets at once.

# 2.Vision and Scope

The SmartPark is a web and mobile system being developed for the City of Houston’s downtown parking garage network. The platform will allow drivers to find available parking, reserve spaces, and make payments in real time. Garage staff and transportation officials will also be able to monitor occupancy, manage statutory pricing and review utilization and accessibility data. The system will be introduced across Houston’s existing downtown garages with reservation and payment features prioritized first and reporting analytics added in later stages.

# 3.Software Requirements Specification

Users: Drivers, city garage staff and administrators, city transportation officials, finance departments, system administrators and third-party payment providers.

System Environment: The platform will include a web application and mobile applications for iOS and Android, supported by a cloud-hosted backend. It will integrate with the city’s existing payment infrastructure, garage occupancy systems and navigation services.

Constraints: The system must follow local laws and regulations, privacy, security and accessibility requirements. Parking prices must support resident discounts and event-based pricing. The project must be completed within the fixed timeline and integrate with the city’s existing payment infrastructure instead of replacing it.

Assumptions: Drivers are assumed to have access to a smartphone or web browser, and the city will provide current pricing and ordinance information needed by the system. Participating garages will have staff capable of manually updating parking availability or internet-connected occupancy sensors.

Functional Requirements

- FR1: The system shall display live open and occupied parking spots on a map.

- FR2: The system shall process digital payments via credit cards and mobile wallets.

- FR3: The system shall guide drivers to their assigned parking spot using GPS

- FR4: The system shall provide garage staff with a dashboard displaying parking occupancy.

- FR5: The system shall allow users to view previous reservations and access digital receipts.

- FR6: The system shall notify users when a reservation is confirmed and when their parking time is close to expiring.

- FR7: The system shall allow users to create an account and log in using email or supported single sign-on options

- FR8: The system shall allow drivers to reserve an available parking space up to 24 hours ahead while preventing the same space from being double-booked.

- FR9: The system shall support different permission levels for admins, managers, and regular team members

- FR10: The platform automatically detects and allows manual check-in via QR codes, or License Plate Recognition (LPR).

Non-Functional Requirements

- NFR1: The system shall handle payment information in compliance with applicable PCI-DSS requirements.

- NFR2: The system shall support at least 5,000 users at the same time.

- NFR3: The system shall maintain at least 99.5% uptime.

- NFR4: New users must be able to navigate the main interface easily without formal training.

- NFR5: All user passwords and project data must be encrypted.

# 4. Work Breakdown Structure

SmartPark’s WBS is consistent with each subsystem tracing back to the Functional Requirements I defined earlier.

- Authentication & User Management

  - Login/Registration

    - Email sign-up and login

    - Single sign-on (SSO) integration

  - Account & Permissions

    - User profile management

    - Role-based permissions

- Parking Availability & Reservations

  - Real-time availability map

    - Live open and occupied spot display

    - ADA-accessible space filtering

  - Reservation system

- Payment & Billing

  - Payment processing

    - Credit card / mobile wallet integration

    - PCI-DSS compliant handling

  - Receipts & History

    - Digital receipt generation

    - Reservation history view

- Navigation & Check-In

  - GPS navigation

    - Turn guidance to assigned spot

  - Garage check-in

    - QR code check-in

    - License Plate Recognition (LPR) check-in

- Admin Dashboard & Reporting

  - Garage staff dashboard

    - Real-time occupancy monitoring

    - Pricing management

  - Reporting & analytics

    - Utilization reports

    - ADA-compliance reports

- Notifications

  - Reservation confirmation

  - Expiration alerts

# Project Timeline

This timeline is the first draft and will be refined as new project management techniques are learned and applied to each WBS module as I progress through the course.

| Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Research & Requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Vision, Scope & SRS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WBS & Timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Authentication & User Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Availability & Reservations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments & Billing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Navigation & Check-In |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Admin Dashboards & Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integration & System Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UAT & Bug Fixes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Delivery & Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Product Backlog and Sprint Planning

The product backlog for SmartPark was organized into four categories, tracked in Jira as Epics: Login, UI, Backend Processes, and Reporting. Each item was written as a user story or technical task following the standard Scrum backlog format.

# Backlog: Login

| ID | Item |
| --- | --- |
| L1 | As a driver, I want to create an account with my email and password, so that I can save my reservation history and payment info. |
| L2 | As a driver, I want to log in using single sign-on (Google/Apple), so that I don't have to remember another password. |
| L3 | As a garage staff member, I want to log in with role-based credentials, so that I only see tools relevant to my job. |
| L4 | As a system administrator, I want to reset a user's password on request, so that locked-out users can regain access. |
| L5 | As a user, I want to see a clear error message when login fails, so that I understand why I couldn't get in. |
| L6 | As a returning user, I want my session to stay active for a set period, so that I don't have to log in every time I open the app. |

# Backlog: UI

| ID | Item |
| --- | --- |
| U1 | As a driver, I want to see an interactive map showing nearby parking garages, so that I can quickly find available options. |
| U2 | As a driver, I want available spaces color-coded by status (available/limited/full), so that I can judge availability at a glance. |
| U3 | As a driver, I want to filter the map to show only ADA-accessible spaces, so that I can find a space that meets my needs. |
| U4 | As a driver, I want to select a garage and see space-level detail, so that I know exactly what I'm reserving. |
| U5 | As a driver, I want a simple checkout screen showing price and time window before confirming, so that I know what I'm paying for. |
| U6 | As a driver, I want to view my reservation history and receipts in one screen, so that I can track past parking activity. |
| U7 | As a driver, I want a 'current reservation' screen showing time remaining, so that I know when I need to return to my car. |
| U8 | As a driver, I want push notifications to appear clearly in-app, so that I don't miss expiration warnings. |
| U9 | As a garage staff member, I want a dashboard showing real-time occupancy for my facility, so that I can monitor usage at a glance. |
| U10 | As a garage staff member, I want to add, edit, or remove a garage listing, so that I can keep facility information accurate. |
| U11 | As a garage staff member, I want to adjust pricing for a specific garage, so that I can apply event-based or resident rates. |
| U12 | As a garage staff member, I want a visual layout of individual spaces within a garage, so that I can see which specific spots are occupied. |
| U13 | As a city transportation official, I want a citywide occupancy dashboard aggregating all garages, so that I can assess downtown parking trends. |
| U14 | As a garage staff member, I want to manually override a space's status (e.g., mark out of service), so that I can account for maintenance or closures. |
| U15 | As a system administrator, I want an admin panel to manage user roles and permissions, so that I can control who accesses which tools. |
| U16 | As a garage staff member, I want a simplified mobile-friendly view of the dashboard, so that I can check occupancy while walking the facility. |

# Backlog: Backend Processes

| ID | Item |
| --- | --- |
| B1 | Implement user authentication service supporting email/password and SSO (Google/Apple). |
| B2 | Build real-time availability sync service that updates space status across all connected clients within 30 seconds. |
| B3 | Implement reservation engine with conflict-checking logic to prevent double-booking of the same space. |
| B4 | Build payment processing integration (credit card and mobile wallet) with PCI-DSS compliant handling. |
| B5 | Implement digital receipt generation and storage tied to each completed transaction. |
| B6 | Build notification service to trigger confirmation and expiration alerts based on reservation time windows |
| B7 | Implement GPS/navigation API integration to generate turn-by-turn directions to a reserved space. |
| B8 | Build check-in verification service supporting both QR code scans and License Plate Recognition (LPR) input. |
| B9 | Build occupancy data ingestion service to pull real-time sensor data (or manual staff updates) per garage. |
| B10 | Implement garage management service supporting add/edit/remove operations on facility records. |
| B11 | Build dynamic pricing engine supporting event-based and resident-discount rate rules. |
| B12 | Implement role-based access control (RBAC) service distinguishing driver, staff, official, and admin permission levels. |
| B13 | Build reporting/analytics engine aggregating utilization data across garages for the reporting dashboard. |
| B14 | Implement ADA-compliance tracking service logging accessible-space usage for city reporting requirements. |
| B15 | Build audit logging service recording manual overrides (e.g., staff marking a space out of service). |
| B16 | Implement data sync service between the city's existing payment infrastructure and the platform's transaction records. |

# Backlog: Reporting

| ID | Item |
| --- | --- |
| R1 | As a driver, I want to view a summary of my total parking spend over time, so that I can track my own expenses. |
| R2 | As a driver, I want to export my reservation history as a PDF, so that I can submit it for expense reimbursement. |
| R3 | As a driver, I want to see how often I've used a specific garage, so that I can decide if a monthly pass would save me money. |
| R4 | As a driver, I want to receive a monthly summary notification of my parking activity, so that I stay aware of my usage patterns. |
| R5 | As a garage staff member, I want a daily utilization report showing peak and off-peak occupancy, so that I can plan staffing accordingly. |
| R6 | As a garage staff member, I want a revenue report broken down by garage and time period, so that I can track facility performance. |
| R7 | As a city transportation official, I want a citywide ADA-compliance report showing accessible-space usage, so that I can meet regulatory reporting requirements. |
| R8 | As a city transportation official, I want a congestion trend report aggregating occupancy across all downtown garages, so that I can assess the effectiveness of the program. |
| R9 | As a finance department member, I want a transaction reconciliation report matching payments to reservations, so that I can verify billing accuracy. |
| R10 | As a garage staff member, I want to export any report as a spreadsheet (CSV/Excel), so that I can share data with stakeholders outside the platform. |
| R11 | As a system administrator, I want a report showing failed login or payment attempts, so that I can monitor for potential security issues. |

# Product Backlog and Sprint Planning

Sprint Goal: A driver can create an account, log in, and see a basic garage availability screen. Sprint 1 was scoped around the minimum vertical slide needed before any other features could be built since every other backlog item depends on a user being authenticated first. The sprint includes:

- All 6 Login items

- 2 supporting UI items: the driver-facing interactive map and the operator occupancy dashboard

- 3 supporting backend items: the authentication service, the occupancy data ingestion service and the role-based access control service

Reservations, payments, receipts and reporting were deliberately excluded from Sprint 1 since none of them are usable until login and basic availability are working end-to-end.

# Sprint 1 Board

Figure 1: SmartPark Sprint 1 Board, Jira

# Risk, Quality and Communication Management

# Risk Identification

Risks were identified across four categories with a minimum of four risks per category covering technical, schedule, financial and people-related concerns for the SmartPark project.

Technical Risks

- Integration with the city’s existing legacy payment infrastructure may be more complex than anticipated.

- Garage occupancy sensor hardware may be unreliable or report inaccurate data.

- Real-time availability sync may fail to scale under high concurrent load.

- Third-party mapping/navigation API may have downtime or breaking changes.

Schedule Risks

- City compliance review process may take longer than the fixed semester timeline.

- Scope creep from newly discovered stakeholder requirements could push back delivery.

- Dependency between Backend and Mapping teams could cause cascading delays if one falls behind.

- Underestimated testing/QA phase could compress the final integration timeline.

Financial Risks

- Third-party payment provider transaction fees could exceed budgeted assumptions.

- Cost of maintaining backup infrastructure for up-time requirements.

- Vendor costs for occupancy sensor hardware could increase mid-project.

- Additional city compliance work could require unplanned spend.

People Risks

- Team member skill gaps in PCI-DSS compliant payment handling could slow implementation.

- A key developer could leave md-project.

- Low team morale from schedule pressure could increase turnover risk.

- Miscommunication between the six dev teams (Mobile, Web, Backend/API, Mapping, Payment Integration, QA) could cause duplicated or conflicting work.

# Risk Register

| ID | Description | Probability | Impact | Owner | Response Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Garage occupancy sensor reports inaccurate data | Moderate(3) | Major(4) | Mapping & Location Services Lead | Mitigate – add manual staff override as fallback | Open |
| R2 | Third-party mapping API downtime | Low(2) | Major(4) | Mapping & Location Services lead | Transfer – SLA with vendor; add secondary API fallback | Open |
| R3 | Real-time sync fails under high load | Moderate(3) | Major(4) | Backend/API Lead | Mitigate – load testing before launch | Open |
| R4 | Legacy payment infrastructure integration complexity | High(4) | Catastrophic(5) | Payment Integration Lead | Mitigate – engage city compliance office early | Open |
| R5 | ADA/compliance review exceeds timeline | Moderate(3) | Major(4) | Project Manager | Mitigate – engage city compliance office early | Open |
| R6 | Cross-team dependency delay | High(4) | Moderate(3) | Project Manager | Mitigate – buffer time in schedule between dependent phases | Open |
| R7 | Payment provider fees exceed budget | Low(2) | Moderate(3) | Finance Billing Lead | Accept – monitor, adjust pricing model if needed | Open |
| R8 | Key developer leaves mid-project | Low(2) | Major(4) | Project Manager | Mitigate – maintain documentation for handoff continuity | Open |
| R9 | Miscommunication between dev teams causes duplicated work | Moderate(3) | Moderate(3) | Scrum Master | Mitigate – enforce daily standups and shared backlog visibility | Open |
| R10 | Team skill gaps in PCI-DSS-compliant payment handling | Moderate(3) | Major(4) | Payment Integration Lead | Mitigate – targeted training or bring in a compliance consultant | Open |

# Product Backlog and Sprint Planning

Meeting Cadence per Team

- Daily stand-up (all 6 dev teams individually): 15 mins, what was done, what’s next, blockers.

- Weekly cross-team progress meeting: Mobile, Web, Backend, Mapping, Payment Integration and QA leads sync on dependencies and integration points.

- Monthly sprint/stakeholder meeting: Product Owner, city transportation officials, and all team leads review sprint outcomes and roadmap.

Reporting Methods by Audience

- City transportation officials (executives): high-level dashboard showing sprint progress, budget status and key risk register items monthly.

- Garage staff/operators: feature-focused demo showing new admin dashboard functionality as it ships biweekly.

- Development teams: detailed task-level updates via Jira board, reviewed daily in standups.

- Finance personnel: budget and cost-tracking report tied to financial risks monthly.

Communication Channel Load

With roughly 6 team leads plus a Product Owner and Scrum Master (8 people) coordinating regularly, the communication channel formula gives N(N – 1) / 2 = 8(7) / 2 = 28 possible communication channels. This is the reasoning behind structuring the cadence above around smaller team-level syncs rather than one large weekly meeting for everyone since channel complexity grows quickly as more people are added.

# Resource and Cost Management

# Roles and Resources

The resource plan assumes a 15-week project at 40 hours a week so a 100% FTE equals 6000 hours. All names are fictional and each development team has a named lead matching the owners assigned in the Risk Register.

| Role | Name | Skill Level | FTE% | Hours | Rate | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | Daniel Oliveira | Senior | 50% | 300 | $60 | $18,000 |
| Product Owner | Sofia Mendes | Senior | 30% | 180 | $65 | $11,700 |
| Scrum Master | Marcus Johnson | Mid | 40% | 240 | $50 | $12,000 |
| Backend Lead | Isabella Romano | Senior | 100% | 600 | $80 | $48,000 |
| Backend Developer | Gabriel Ferreira | Mid | 100% | 600 | $65 | $39,000 |
| Mobile Developer | Lucas Moreira | Senior | 100% | 600 | $80 | $48,000 |
| Mobile Developer | Beatriz Costa | Mid | 100% | 600 | $65 | $39,000 |
| Web Developer | Nathan Brooks | Mid | 100% | 600 | $65 | $39,000 |
| Web Developer | Andre Carvalho | Junior | 100% | 600 | $45 | $27,000 |
| Mapping & Location Lead | Chloe Anderson | Senior | 100% | 600 | $80 | $48,000 |
| Payment Integration Lead | Mateo Rodriguez | Senior | 100% | 600 | $80 | $48,000 |
| QA Engineer | Camila Santos | Mid | 100% | 600 | $50 | $30,000 |
| QA Engineer | Ethan Williams | Junior | 100% | 600 | $40 | $24,000 |
| UX Designer | Charles Oliveira | Mid | 50% | 300 | $60 | $18,000 |
| DevOps Engineer | Alex Pereira | Senior | 50% | 300 | $80 | $24,000 |
| Compliance SME (ADA/PCI) | Alexandre Pantoja | Senior | 20% | 120 | $90 | $10,800 |
| Total |  |  |  | 7,440 |  | $484,500 |

# Resources and Cost Plan (Bottom-Up)

A bottom-up estimate was chosen because it has the right technique for the proposal and contracting stage which fits a city RFP. Each cost is built from the hours and rates above plus itemized non-labor costs.

| Item | Category | Calculation | Total |
| --- | --- | --- | --- |
| Labor | Labor | From the resource plan in 8.1 | $484,500 |
| Overhead/benefits | Overhead | 20% of labor | $96,900 |
| Cloud hosting | Infrastructure | $3,000/month x 4 months | $12,00 |
| Mapping/navigation APIs | APIs | $1,500/month x 4 months | $6,000 |
| Payment sandbox/test fees | APIs | $500/month x 4 months | $2,000 |
| Licenses and tools | Tools | One-off | $4,000 |
| Occupancy sensor test hardware | Hardware | One-off | $12,000 |
| PCI-DSS security assessment | Compliance | One-off | $15,000 |
| ADA/legal compliance review | Compliance | One-off | $8,000 |
| PCI-DSS training | Training | One-off | $3,00 |
| Subtotal |  |  | $643,400 |
| Contingency | Reserve | 15% of subtotal | $96,510 |
| GRAND TOTAL |  |  | $739,910 |

The 15% contingency falls within the 5-20% range from the lecture. The higher end was chosen because risk R4 in the Risk Register (legacy payment infrastructure integration) is rated high probability and catastrophic impact.

| Month | Labor | Overhead | Non-Labor | Contingency (15%) | Total |
| --- | --- | --- | --- | --- | --- |
| Month 1 | $121,125 | $24,225 | $12,000 | $23,602.50 | $180,952.50 |
| Month 2 | $121,125 | $24,225 | $17,000 | $24,352.50 | $186,702.50 |
| Month 3 | $121,125 | $24,225 | $13,000 | $23,752.50 | $182,102.50 |
| Month 4 | $121,125 | $24,225 | $20,000 | $24,802.50 | $190,152.50 |
| Total | $484,500 | $96,900 | $62,000 | $96.510 | $739,910 |

Non-labor spending follows the project milestones: licenses and training in Month 1, sensor test hardware in Month 2, the ADA/legal review in Month 3 and the PCI-DSS security assessment in Month 4 ahead of launch. Cloud, API and payment sandbox costs recur monthly.

# RACI Matrix

Roles: PM (Project Manager), PO (Product Owner), SM (Scrum Master), TL (Backend/API Lead acting as tech lead), Dev (Mobile, Web, Backend, Mapping and Payment developers), QA, UX, DevOps and SME (Compliance). R = Responsible, A = Accountable, C = Consulted, I = Informed. Each row has exactly one A, “A/R” means the same role both does the work and approves it.

| Deliverables | PM | PO | SM | TL | Dev | QA | UX | DevOps | SME |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirement & SRS | R | A | I | C | C | C | C | I | C |
| UX Design & Prototypes | I | A |  | C | C | I | R | I | C |
| Architecture & System Design | I | C | I | A | R | I | I | C | I |
| Sprint Planning & Backlog | C | A | I | C | C | C | I | I | I |
| Feature Implementation | I | C | R | A | R | C | C | C | I |
| Payment Integration & PCI-DSS | A | C | I | C | R | C | I | C | C |
| ADA & City Compliance Review | A | C | I | I | I | C | C | I | R |
| System Testing | I | C | I | C | C | A/R | I | I | I |
| Deployment & Release | I | C | I | C | C | C | I | A/R | I |
| Budget & Cost Tracking | A/R | C | I | I | I | I | I | I | I |

The Finance/Billing Lead named in the Risk Register is a city-side role so it is not part of this project team’s payroll or RACI.